## Sheet3
2010 | September | Courses
October
November
December
2011 | January
| February |  | Studying Web Services, Game Theory, Mechanism Design and Cooperative Game Concepts
March
April
May
June
July
| August |  |  | Preparation for Comprehensive Exam
September
October
| November |  |  | Passed the Comprehensive Exam
| December |  |  |  | Submitted a Paper to the 10th International Conference on Service Oriented Computing (ICSOC 2012); "Analyzing Coopetition Strategies of Services within Communities" (Accepted)
2012 | January
February
March
April
May
June
| July |  | Submitted a Journal Paper to the the International Journal of Web and Grid Services; "A Decision Making Mechanism for Web Services Competitive and Cooperative Strategies within Communities"
August
| September | Proposed Noval Cooperative Game Theory Base Algorithms, and Started Coding the Simulation
October
November
December
2013 | January |  | Submitted a Paper to 10th International Conference on Services Computing; "Efficient Coalition Formation for Web Services" (Accepted)
February
| March |  |  |  | Submitted a Journal Paper to the the International Journal of Web and Grid Services; "A Decision Making Mechanism for Web Services Competitive and Cooperative Strategies within Communities"
April
May
June
| July |  | Analyzing convexity condition for Web Service type of linear valuation functions
August
| September | Preparing and writing Ph.D. Proposal |  | Analysing and Writing Simulation Code for Kernel, Nucleus, Bargaining Solution Concepts | Developing an open source, Java based Tool, with UI (probably based on JavaFX) for solving Core and Shapely solution concepts based on different input valuation functions.
October
November
| December | Ph.D proposal defense
2014 | January | Ph.D. seminar
February
March
April
May
June
July
August
| September | Thesis writing and defense
October
November
December
|  | Work done | Work in progress | Work to be done